## Goal 1
GOAL 1: Decrease shelter stays by increasing rapid rehousing to stable housing.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Identify all housing resources for people who are below 30% AMI. | Provide information to the Landlord association on HPIN and our resources | Solutions Beyond Shelter Housing Committee | December 2012 | Medium | yes | Met with Landlord Association several times
| Map out all available housing resources | SBS Housing Committee | December 2012 | High | yes | Housing resources are mapped and a community pamphlet has been developed
| Create a Landlord registry of those who can work with families/individuals with barriers (no credit checks, no background checks, will work with advocate). | SBS Housing Committee | May 2013 | Medium | yes | Recevied landlord list from LHA. Homestead has a listing for landlords willing to work with tenant education.
Identify all emergency shelters and ensure they are represented at HPIN | Map out all available shelter resources, including ES and TH | Housing Committee and SBS Housing Committee | December 2012 | High | yes | All available shelter resources are identified
| Create a baseline of shelter stays for all ES and TH programs. | Housing Committee | January 2013 | Medium | in progress | Moved to Data Committee, will be completed by August 2013 and a HIGH priority
Identify all emergency financial resource providers and invite them to meet with HPIN. Inform them about the Rapid Re-Housing approach to ending homelessness | Map out all available emergency financial resource providers | SBS Housing Committee | December 2012 | Medium | yes | Moved to Interagency Cmt: An "upfront" funder has been identified
| Encourage that all are attending HPIN meetings | HPIN Education Committee | December 2012 | Medium | yes | Several new members have been added.
| Apply for any additional emergency financial resources for rapid re-housing. | LTHC | ASAP | High | yes | Additional Rapid Re-Housing Funds for FY16, over $450,000!
Solutions Beyond Shelter is our Community Plan to end homelessness
HPIN is the Homelessness Prevention and Intervention Network, which is the Region 4 Planning Council
For questions, please contact Marie Morse, Chair of HPIN, marie@homesteadcs.org

## Goal 2
GOAL 2: Reduce recidivism of households experiencing homelessness
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with IHCDA to establish a HMIS report to provide community level accurate data for recidivism. | Ask IHCDA to create a report to provide this information. | HMIS User Group | 2013 | low | no | IHCDA meeting with group in August 2013

## Goal 3
GOAL 3: Decrease the number of Veterans experiencing homelessness.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with IHCDA to establish a HMIS report to provide community data to accurately reflect the number of Veteran's | Ask IHCDA to create a report to provide this information. | HMIS User Group | December | medium | no | Moved to December 2013
2012
Establish relationship with staff from | Invite representative to HPIN meeting. | HPIN Chair | immediate | high | yes | Staff attending HPIN
the Indiana Veteran's Home in West
Lafayette
Have HPIN representative serve on theSteering Committee for the Homeless Veteran's Summit | Ask HVS Steering Committee if someone from HPIN can serve on the committee | HPIN Chair | Immediate | High | yes | Adam Murphy served on the steering cmt
Have HPIN represented at the Stand Down taking place in November 2012 | Ask Martina with MFRI if HPIN can have a booth | HPIN Education Committee | Immediate | High | yes | Did not have a HPIN booth, but many members participated
Investigate SSVF funding opportunity | LTHC applied for and has received funding for 75 Veterans FY14, FY15, and FY16 | LTHC | Immediate | High | yes
Obtain HUD VASH Vouchers | Lafayette Housing Authority has obtained 18 Vouchers | LHA/LTHC/VA | 2014-2015 | High | n/a

## Goal 4
GOAL 4: Decrease the number of persons experiencing Chronic Homelessness.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with IHCDA to establish a HMIS report to provide community level accurate data for chronic homelessness | Ask IHCDA to create a report to provide this information. | HMIS User Group | ASAP | High | no | IHCDA meeting with Data
cmt in August 2013
Develop additional PSH or S+C opportunities within our Region | Apply for funding opportunities that may be available | LTHC | 2015-03-01 | High | yes | Added 24 PSH Units for Singles
|  |  | 2016-01-01 |  |  | Will add 11 units of PSH for
families

## Goal 5
GOAL 5: Decrease the number of homeless households with children.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with IHCDA to establish a HMIS report to provide community level accurate data for the number of homeless households with children | Ask IHCDA to create a report to provide this information. | HMIS User Group | ASAP | HIgh | no | IHCDA meeting with Data
cmt in August 2013
Create Permanent Supportive Housing for Homeless Families with Children (PSH is only for those with multiple barriers) | LTHC will repurpose their TH units to 11 PSH | LTHC | ASAP | High | no | January 2016
Find permanent housing for families with low barriers. | Create a Reduced Barriers Landlord Registry | SBS Housing Committee | 2013 | Medium | yes | Recevied landlord list from LHA. Homestead has a listing for landlords willing to work with tenant education.
| Apply for any additional emergency financial resources for rapid re-housing. | LTHC | ASAP | High | yes | DONE
Increase DVIP beds to 30 | Apply for funding and opportunities | SBS Housing Committee | 9/13 | High | n/a | Stategy added in 2013

## Goal 6
GOAL 6: Increase the percentage of participants in Continuum of Care funded projects that are employed at exit to 38 percent or higher
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Talk with both LTHC and Family Crisis Shelter, the only 2 SHP funded projects in our continuum, and ensure that their employment at exit rate is 38% or higher. | Ask both to submit information | HPIN Chair | 2012 | High |  | LTHC is no longer receiving CoC Funding from Balance of State for the Family Program.
regarding their employment status
at exit.
Ensure Homeless clients have a way to get their messages from employers and/or landlords | Establish Community Voice Mail System | SBS Employment Committee | 2012/2013 | Medium | yes | LTHC & Family Promise helps their clients access Assurance Phones so community voice mail is no longer needed
Improve collaboration with employers, trainers, and education. | Invite representatives from Voc Rehab, ASI, Employabilities, LARA to attend HPIN | HPIN Education Committee | 2012 | Medium | no | moved to HPIN steering cmt and changed to 2013
| Create day sleeping opportunities for those who are working nights and have no shelter | LTHC | 2012 | High | no | LTHC has two bunk beds in the Homeless Services Program

## Goal 7
GOAL 7: Increase persons experiencing homelessness access to mainstream resources
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with IHCDA to establish a HMIS report to provide community level accurate data for the number of homeless who are and are not accessing mainstream resources upon discharge | Ask IHCDA to create a report to provide this information. | HMIS User Group | ASAP | High | in progress | Should be completed in 2013
Increase the number of people accessing mainstream benefits | Ensure CM staff is trained on Benefits Bank, | HPIN Housing Committee | 2012 | Medium | yes | Staff has been trained. Still need data from above strategy
benefits.gov, or other benefit websites
| Invite a DFR representative to attend HPIN meetings | HPIN Education | 2012 | Medium | yes | Michael Guest from the DFR will begin to attend HPIN meetings in 2nd half of 2013

## Goal 8
GOAL 8: Collaborate with local education agencies to assist in the identification of homeless families and inform them of their eligibility for McKinney-Vento education services.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Ensure that the McKinney Vento liaison in each school district in our region, is informed about the shelters and the legal rights of the children. | Create a letter to distribute to all McKinney Vento liaisons to explain the law, and the local resources that provide assistance. | HPIN Education Committee | 2013 | Medium | no | Letter by email will be sent to principals asking them to forward to their entire staff: Aimee Jacobsen will get
| Invite School Liasons to join HPIN | HPIN Steering Committee | 2013 |  | new for 2013

## Goal 9
GOAL 9: Improve homeless outreach and triage to housing and services.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Work with HPIN members to ensure homeless outreach is being provided | Talk with MHA Day Shelter staff, MHA employs one FTE that provides Homeless Outreach | HPIN Housing Committee | 2013 | Medium | yes | MHA has received a ESG grant to begin an Outreach program and is working with the Laf & WL Police Dept to implement
Work with all HPIN members to ensure homeless triage to housing and services is done appropriately | LTHC was officially designated the Coordinated Entry to do intake, assessment and triage | LTHC | March 2014 |  |  | Done!

## Goal 10
GOAL 10: Improve HMIS data quality and coverage, and use data to develop strategies and policies to end homelessness.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Assign a member of Region 4 to participate in the IHCDA HMIS User Group | HPIN Chair will assign someone | HPIN HMIS Users committee | ASAP | High | yes | Jennifer Layton is our representative for the IHCDA HIMS User group
Assign a member of Region 4 to participate in the IHCDA HMIS Analytic Group | HPIN Chair will assign someone | HPIN HMIS Users committee | ASAP | High | n/a | The State decided to not have this group
Work with IHCDA and HMIS to establish baseline data for all agencies that are participating in HMIS for Region 4 | Invite IHCDA staff to HPIN User Group meeting to communicate needs and concerns | HPIN HMIS Users committee | ASAP | High | on going | IHCDA did meet with the user group in 2013
| Develop a Community Dashboard Report | HPIN Data Committee | 2013 | High |  | new for 2013

## Goal 11
GOAL 11:. Develop effective discharge plans and programs for individuals leaving State Operated Facilities at risk of homelessness.
Stategy | Action Steps | Persons / Organizations Responible | Time Frame | Priority | Accomplished | 2013 Update
Investigate the current discharge policies/procedures for state operated facilies | Work with IHCDA on state facilities | HPIN IHCDA Liaison | 2013 | medium | no
| Work with St. Elizabeth and River Bend | SBS Health Committee | 2013 | Low | no | move to medium priority
on their policies.
Work with law enforcement on their
| discharge policies | SBS Re-Entry Committee | 2013 | Low | no | move to medium priority
| Investigate the State law requirements | Aimee Jacobsen | 2013 | Med | no | new for 2013